# FA26SE083 — PROJECT SCHEDULE

| Name | Duration | Start | Finish | Predecessors | Resource Names | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 1 FA26SE083 — FSCM Project Schedule | 137 days | 04/08/2026 | 18/12/2026 |  | All members | S1–S4: 18 Oct–12 Dec; S5 backup: 13–18 Dec. 149 platform tasks, all To Do. Original preparation phases retained. |
| 2 Project Start | 0 days | 04/08/2026 | 04/08/2026 |  | All members | Start of the original four-week preparation period. |
| 3 Initiation & Early Preparation (Stage 1) | 28 days | 04/08/2026 | 31/08/2026 | 2 | All members | Preparation weeks 1–4, before the official project term. |
| 4 Kick-off, role assignment and domain research | 14 days | 04/08/2026 | 17/08/2026 | 2 | All members; Nhan, Khiet | Deliverables: Team Charter, responsibility allocation and Domain Research Note. |
| 5 Technical spikes: concurrency, offline queue and Redis | 21 days | 04/08/2026 | 24/08/2026 | 4SS | Nhan, Son, Khiet | Deliverables: experimental repository and feasibility findings; retained from the original preparation plan. |
| 6 Draft scope, business analysis, ERD and architecture | 21 days | 11/08/2026 | 31/08/2026 | 4SS | All members | Deliverables: draft scope and MoSCoW priorities, business analysis, ERD and architecture. |
| 7 Set up repositories, CI, task board and wireframes | 14 days | 18/08/2026 | 31/08/2026 | 5SS | Nhan, Son; Hai, Hoang | Deliverables: buildable base code, Azure Board, Portal and Mobile wireframes. |
| 8 Planning & Requirements (Stage 2) | 21 days | 01/09/2026 | 21/09/2026 | 6;7 | All members | Original planning period retained for scope definition and Review 1 preparation. |
| 9 Finalize Scope Statement, MoSCoW and MVP | 14 days | 01/09/2026 | 14/09/2026 | 6 | All members | Deliverables: agreed scope boundaries and prioritized feature list. |
| 10 Business analysis v1.0 and preliminary API specification | 21 days | 01/09/2026 | 21/09/2026 | 9SS | Khiet, Hai; Nhan | Deliverables: business processes, use cases and preliminary API contracts. |
| 11 Architecture, ERD and Data Dictionary | 14 days | 01/09/2026 | 14/09/2026 | 6 | Nhan | Deliverables: Architecture Diagram, batch-level ERD and Data Dictionary. |
| 12 Database migrations, base code and sprint planning | 14 days | 08/09/2026 | 21/09/2026 | 7 | Nhan, Son; All members | Deliverables: migrations from an empty database, repository/CI setup, schedule and initial assignments. |
| 13 Review 1 — Scope & MVP | 0 days | 21/09/2026 | 21/09/2026 | 9;10;11;12 | All members | Original milestone retained. Deliverables: scope package, Review 1 slides and MVP demonstration plan. |
| 14 Software Design (Stage 3) | 54 days | 08/09/2026 | 31/10/2026 | 11SS | Nhan, Khiet, Hai | Design refinement continues through S1 to support the revised implementation baseline. |
| 15 Refine business processes, use cases and SRS | 54 days | 08/09/2026 | 31/10/2026 | 10SS | Khiet, Hai | Deliverables: updated business analysis, SRS and allocation flow aligned with the task tracker. |
| 16 Finalize module design, sequences and ERD | 14 days | 18/10/2026 | 31/10/2026 | 11;13 | Nhan | Deliverables: module and sequence diagrams, final ERD and migration updates. |
| 17 Finalize API contracts and core test cases | 14 days | 18/10/2026 | 31/10/2026 | 10;13 | Nhan, Khiet; All members | Deliverables: agreed API contracts and test cases for authentication, orders, allocation and inventory. |

| Name | Duration | Start | Finish | Predecessors | Resource Names | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 18 Implementation (Stage 4) | 56 days | 18/10/2026 | 12/12/2026 | 13 | All members | S1/S2/S3/S4: 32/43/67/7 tasks. Backend 73, Portal 46, Mobile 30. Use Task_Tracking sprint assignments. |
| 19 Sprint 1 — Foundation & master data | 14 days | 18/10/2026 | 31/10/2026 | 13;16SS;17SS | All members | 32 tasks: Backend 16, Portal 13, Mobile 3. Access control, master data and transport/ETA foundation. |
| 20 Authentication, authorization and user profiles | 14 days | 18/10/2026 | 31/10/2026 | 19SS | Khiet, Hai, Son, Hoang | F08–F13: Portal/Mobile login, role/scope checks, seeded Admin, user management and Mobile profiles. |
| 21 Products, warehouses and retailer master data | 14 days | 18/10/2026 | 31/10/2026 | 20SS | Khiet, Hai, Son, Hoang | F14–F19, F22–F23: categories, product lifecycle/cloning, warehouses, regions, Sales groups, retailer potential, MLOR and credit terms. |
| 22 Transport rules, distances and shared ETA | 14 days | 18/10/2026 | 31/10/2026 | 21SS | Nhan | F54–F56: effective-dated transport rules, warehouse–retailer/warehouse distances and shared ETA snapshots. |
| 23 Sprint 2 — Orders, allocation & warehouse flow | 14 days | 01/11/2026 | 14/11/2026 | 19 | All members | 43 tasks: Backend 21, Portal 11, Mobile 11. Online orders, allocation, approval, picking and dispatch confirmation. |
| 24 Retailer onboarding, promotions, orders and payments | 14 days | 01/11/2026 | 14/11/2026 | 23SS | All members | F20–F21, F24–F28, F32, F37, F63: retailer onboarding, promotions/quotes, online orders, region checks, order history and COD/prepayment. |
| 25 Allocation engine, stock holds and order approval | 14 days | 01/11/2026 | 14/11/2026 | 23SS;24SS;22 | Nhan | F33–F36, F38: B1–B4 allocation with batch/distance/ETA/MLOR, stock holds, concurrency, trace, approval/rejection/cancellation and weights. |
| 26 Receipts, batches, QR labels, picking and dispatch | 14 days | 01/11/2026 | 14/11/2026 | 23SS;21;25SS | Khiet, Hai, Son, Hoang | F39–F45: goods receipts, batches, QR printing, expiry tracking, picking lists, QR scan/split, dispatch confirmation and label lookup. |
| 27 Review 2 — Design & Sprint 1 Progress | 0 days | 26/10/2026 | 26/10/2026 | 14SS;19SS | All members | Original review date, within S1: design and foundation progress. Core flow due 14 Nov; offline sync due 28 Nov. |
| 28 Sprint 3 — Offline, delivery & business completion | 14 days | 15/11/2026 | 28/11/2026 | 23 | Unassigned | 67 tasks: Backend 33, Portal 20, Mobile 14; PICs blank. Loyalty/KPI/reporting follow task rows (S3), rather than the S4 summary. |
| 29 Offline synchronization and inventory expiry control | 14 days | 15/11/2026 | 28/11/2026 | 28SS | Unassigned | F29–F31, F46–F53: SQLite snapshot/queue, idempotent sync/status tabs; shelf-life discounts, write-off, transfers, rotation, settings and backtests. |
| 30 Delivery, retailer receipt, complaints and receivables | 14 days | 15/11/2026 | 28/11/2026 | 28SS;26 | Unassigned | F57–F62, F64–F68: vehicles/personnel, delivery assignment/cost, QR receipt, complaints, receivables, single settlement and overdue balances. |
| 31 Loyalty, KPI, rankings, dashboard and notifications | 14 days | 15/11/2026 | 28/11/2026 | 28SS;30SS | Unassigned | F69–F81: loyalty, gifts/redemption, KPI, net-revenue/product rankings, dashboard, in-app/push. Credit-order points await payment. |
| 32 Verification — Sprint 4 (Stage 5) | 14 days | 29/11/2026 | 12/12/2026 | 28 | Unassigned | 7 tasks: Backend 3, Portal 2, Mobile 2. F82–F84: demo data, integration tests, fixes and final deployment. |
| 33 Review 3 — Progress Demo & Mock Defense | 0 days | 16/11/2026 | 16/11/2026 | 23;28SS | All members | Original date, at S3 start: demo S1/S2 and available S3 work. Remaining features due 28 Nov; integration testing due 12 Dec. |
| 34 Seed demo data and test end-to-end workflows | 14 days | 29/11/2026 | 12/12/2026 | 32SS | Unassigned | F82–F83: seed demo data; test order → allocation → approval → picking → dispatch → receipt → receivables/points, plus offline Mobile flows. |
| 35 Transition (Stage 6) | 32 days | 17/11/2026 | 18/12/2026 | 33 | All members | Prepare documents, deployment and defense materials alongside development; S5 provides a contingency window after S4. |
| 36 Fix defects and deploy the final release | 14 days | 29/11/2026 | 12/12/2026 | 34SS | Unassigned | F84: Backend fixes/migration/deployment; Portal fixes and Vercel deployment; Mobile fixes and demo APK. PICs unassigned. |
| 37 Thesis, manuals and defense preparation | 28 days | 17/11/2026 | 14/12/2026 | 33;35SS | All members; Hai, Hoang; Nhan, Son | Original document owners retained. Thesis/manuals by 7 Dec; deployment guide, README, slides, Q&A and rehearsal by 14 Dec. |
| 38 Sprint 5 — Contingency / backup window | 6 days | 13/12/2026 | 18/12/2026 | 32;36 | All members | S5 backup from Sprints; no assigned feature tasks. Defense remains 14 Dec. Use of 15–18 Dec requires alignment with the defense schedule. |
| 39 Final Project Package & Defense | 0 days | 14/12/2026 | 14/12/2026 | 34;36;37 | All members | Original defense date. Deliverables: thesis, source/README, manuals, deployment guide, APK/online demo, slides, tests and records. |