## WBS
PROJECT WORK BREAKDOWN STRUCTURE
# | Function/Screen | Feature | Level* | Function/Screen Details | Planned | Status
1 | View dashboard (order, revenue, sale leaderboard) | FSCM | Medium | Estimated effort: 8 man-days
2 | Manage user account | FSCM | Simple | Estimated effort: 8 man-days
3 | Manage metadata | FSCM | Simple | Estimated effort: 10 man-days
4 | Manage promotion rule | FSCM | Medium | Estimated effort: 10 man-days
5 | Manage retailer data and policy | FSCM | Simple | Estimated effort: 6 man-days
6 | Process purchase order | FSCM | Medium | Estimated effort: 10 man-days
7 | Confirm order payment with QR code / bank transfer | FSCM | Simple | Estimated effort: 5 man-days
8 | Process retailer complaint | FSCM | Simple | Estimated effort: 6 man-days
9 | Manage sale group | FSCM | Simple | Estimated effort: 8 man-days
10 | View sale group dashboard (order, retailer, revenue) | FSCM | Simple | Estimated effort: 5 man-days
11 | View sale area and list of retailer in their sale group | FSCM | Simple | Estimated effort: 7 man-days
12 | View product catalog and inventory balance | FSCM | Simple | Estimated effort: 5 man-days
13 | Cache product catalog and inventory balance for offline access | FSCM | Medium | Estimated effort: 9 man-days
14 | Create purchase order (with or without internet) | FSCM | Simple | Estimated effort: 7 man-days
15 | Sync purchase order when internet connection available | FSCM | Hard | Estimated effort: 15 man-days
16 | Tracking order life-cycle status and receive notification | FSCM | Medium | Estimated effort: 10 man-days
17 | Confirm pay in cash purchase order | FSCM | Simple | Estimated effort: 4 man-days
18 | View order history (personal and sale group) | FSCM | Simple | Estimated effort: 4 man-days
19 | View sale leaderboard | FSCM | Simple | Estimated effort: 4 man-days
20 | View sale dashboard (retailer, order, revenue) | FSCM | Medium | Estimated effort: 7 man-days
21 | View order detail and order history | FSCM | Simple | Estimated effort: 4 man-days
22 | Scan QR code to confirm delivery order | FSCM | Hard | Estimated effort: 10 man-days
23 | View dashboard (order and spending) | FSCM | Medium | Estimated effort: 6 man-days
24 | Receive order status and notification | FSCM | Medium | Estimated effort: 6 man-days
25 | File retailer complaint | FSCM | Medium | Estimated effort: 7 man-days
26 | Tracking goods receive note (GRN) life-cycle status and receive notification | FSCM | Medium | Estimated effort: 14 man-days
27 | View inventory balance and life-cycle status (Normal/Near-date/Expired) | FSCM | Simple | Estimated effort: 5 man-days
28 | Process picking list to export batches | FSCM | Hard | Estimated effort: 19 man-days
29 | Block expiry batches | FSCM | Simple | Estimated effort: 4 man-days
30 | Cronjob to track batches, block expiry batches, mark near-date batches | FSCM | Hard | Estimated effort: 10 man-days
31 | Handle concurrent allocation using optimistic locking and automatic batch fallback | FSCM | Hard | Estimated effort: 16 man-days
32 | Run multi-warehouse batch picking for each SKU when receive order | FSCM | Hard | Estimated effort: 18 man-days
33 | Pick promotion when create purchase order | FSCM | Hard | Estimated effort: 12 man-days
34 | Notify when status change with audit trail | FSCM | Medium | Estimated effort: 8 man-days
35 | Manage product category and published SKU lifecycle | FSCM | Medium | Estimated effort: 4 man-days
36 | Manage warehouse transfer note and stock replenishment suggestion | FSCM | Hard | Estimated effort: 5 man-days
37 | Manage vehicle and delivery person master data | FSCM | Simple | Estimated effort: 3 man-days
38 | Assign vehicle and delivery person to order | FSCM | Simple | Estimated effort: 3 man-days
39 | Manage batch expiry discount and reminder | FSCM | Medium | Estimated effort: 4 man-days
40 | Manage deferred payment and overdue orders | FSCM | Medium | Estimated effort: 3 man-days
41 | Manage loyalty program, points and gift redemption | FSCM | Hard | Estimated effort: 5 man-days
42 | Manage retailer potential assessment and sales area restriction | FSCM | Medium | Estimated effort: 3 man-days
43 | View best-selling products and sales KPI after promotion | FSCM | Medium | Estimated effort: 2 man-days
44 | Configure weighted batch allocation scoring | FSCM | Medium | Estimated effort: 3 man-days

## Issues
PROJECT ISSUES
# | Issue | Potential Impact | Priority | Owner | Open Date | Close Date | Status | Notes
1 | Report 3 - Phần 3 còn thiếu screenflow diagram, màn hình cho từng feature 3.2 -> 3.13, physical erd chưa chốt - Phần 4 mới liệt kê các non-functional, chưa đi vào chi tiết - Phần 5 liên quan đến business rule - Mục nào còn thiếu sẽ có chữ PENDING |  | Low | Tran Ngoc Khiet | 2026-10-12 | 2026-10-14 | Closed | Nhân làm 5.1 Khiết làm 5.2, 5.3 Sơn làm 3 4 pending chờ 5
2 | File Project Weekly Report_GroupName.xlsx chưa cập nhật thường xuyên |  | Medium | Tran Ngoc Khiet | 2026-10-12 | 2026-10-15 | Closed | Võ Minh Sơn cập nhật
3 | Report 4 yêu cầu kiểm tra các features và thuật toán ở report 3 để vẽ diagram |  | High | Tran Ngoc Khiet | 2026-10-13 | 2026-10-16 | Closed | Đã chia module, Sơn + Hoàng vẽ sequence diagram, Khiết + Hải vẽ class diagram
4 | Thiếu chi tiết dashboard cho các role khác ngoài admin |  | Medium | Tran Ngoc Khiet | 2026-10-16 | 2026-10-21 | Closed | Admin làm trước, các role khác để nice to have
5 | Chưa chốt dùng map của bên nào |  | High | Tran Ngoc Khiet | 2026-10-17 | 2026-10-21 | Closed | Google Maps
6
7

## Defects
PROJECT DEFECTS
Feature | Function/Screen | Tester | Defect Description | Assign To | Status | Notes

## Q&A
PROJECT Q&A
Date | Question | By | Priority | Status | Note (answer, other notes)