## Schedule
CAPSTONE PROJECT SCHEDULE
# | Duration | Method | Task | Document
1 | Week 1 | Project Presentation | 1. Scope (Major Feature) 2. Context Diagram 3. System Reference 4. Core Flow (Swimlane) 5. Project Team 6. Technology
2 | Week 2 | Project Presentation | 1. Confirm Scope 2. Confirm Context Diagram 3. Confirm Core Flow 4. Prototype (Core Flow, Figma)
3 | Week 3 | Project Presentation | 1. Confirm Prototype (Core Flow, Figma) 2. Screen Flow Diagram 3. ERD 4. Project Solution * Review 1 | Report1_Project Introduction.docx (Required)
4 | Week 4 | Project Presentation | 1. Confirm Screen Flow Diagram 2. Confirm ERD 3. DB 4. State Transition Diagram 5. Prototype (Full, FE)
5 | Week 5 | Project Presentation | 1. Confirm DB 2. Confirm State Transition Diagram 3. Confirm Prototype (Full, FE) 4. Sample Data
6 | Week 6 | Project Presentation | 1. Demo Core Flow | Report2_Project Management Plan.docx (Required) Report3_Software Requirement Specification.docx (Required)
7 | Week 7 | Project Presentation | 1. Demo Core Flow * Review 2
8 | Week 8 | Project Presentation | 1. Final Demo Core Flow
9 | Week 9 | Project Presentation | 1. Demo Full
10 | Week 10 | Project Presentation | 1. Demo Full
11 | Week 11 | Project Presentation | 1. Demo Full
12 | Week 12 | Project Presentation | 1. Final Demo Full 1 | Report4_Software Design Document.docx (Required) Report5_Test Documentation.docx (Required) Report5_Test Report.xlsx (Required) Report6_Software User Guides.docx (Required)
13 | Week 13 | Project Presentation | 1. Final Demo Full 2 * Review 3
14 | Week 14 | Project Presentation | 1. Final Presentation Slide 2. Submit Documents | Report7_Final Project Report.docx (Required) Database Scripts (Required) Source Codes & Related Files (Required) Presentation Slides (Required) Report3_Project Tracking.xlsx (Optional) Report5_Unit Test.xlsx (Optional) Demo Video (Optional)
15 | Week 15 | Project Presentation | 1. Capstone Defence 1