CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

Version 1.5

– Ho Chi Minh City, October 2026 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	5

1. Overview	5

1.1 Scope & Estimation	5

1.2 Project Objectives	7

1.3 Project Risks	9

2. Management Approach	10

2.1 Project Process	11

2.2 Quality Management	12

2.3 Training Plan	13

3. Project Deliverables	14

4. Responsibility Assignments	14

5. Project Communications	16

6. Configuration Management	17

6.1 Document Management	17

6.2 Source Code Management	18

6.3 Tools & Infrastructures	18

# I. Record of Changes

| Date | A, M, D * | In charge | Change Description |
| --- | --- | --- | --- |
| 15/09/2026 | A | Tran Ngoc Khiet | Version 1.0 Add: - 1.1 Scope & Estimation - 1.2 Project Objectives |
| 23/09/2026 | A, M | Tran Ngoc Khiet | Version 1.1 Modified: - 1.1 Scope & Estimation: Update functions based on new project details - 1.2 Project Objectives: Add testing plan and project man-days allocation Add: - 1.3 Project Risks - 2. Management Approach - 2.1 Project Process - 2.2 Quality Management - 4. Responsibility Assignments - 5. Project Communications - 6. Configuration Management - 6.1 Document Management - 6.2 Source Code Management - 6.3 Tools & Infrastructures |
| 27/09/2026 | A, M, D | Tran Ngoc Khiet | Version 1.2 Add: - 2.3 Training Plan - 3. Project Deliverables (file) Modified: - 1.1 Scope & Estimation: Update new scope base on Coreflow_v1.1.xlsx - 4. Responsibility Assignments: Update new responsibility and assign to members Deleted - 1.1 Scope & Estimation: Delete old scope features |
| 27/09/2026 | A, M | Truong Le Huy Hoang | Revised role responsibilities and corrected spelling errors. Add training plan area Flutter |
| 11/10/2026 | A, M | Tran Ngoc Khiet | Version 1.3 Add: - 1.1 Scope & Estimation: New features after Review 1 - 4. Responsibility Assignments: New tasks Modified: - 1.2 Project Objectives: Planned effort and contingency - 1.1 Scope & Estimation: Rebalance effort to 323 man-days and 14 man-days contingency - Shorten some WBS Items |
| 27/10/2026 | A, M, D | Truong Le Huy Hoang | Version 1.4 Add: Current delivery and quality targets; allocation/pricing, financial and integration risks; deliverable owners; CI/CD and baseline controls. Modify: Sections 1–6 against Registration v1.8, Report 1 v1.6, SRS v1.5, Task Tracking Scope V10, Project Tracking, Report 5 v1.1, TEAM_SETUP and Review 2 guidance. Reconcile WBS and capacity; align task responsibilities with PICs. Delete: Internal transfers/replenishment and automatic offline submission from the planned scope. Project Schedule remains a separate companion document. Unresolved cross-document decisions are identified for baseline alignment. |
| 28/10/2026 | M | Tran Ngoc Khiet | Version 1.5: Align scope, WBS descriptions, integration tests and baseline controls with Registration v1.8 and Report 1 v1.7. Confirm 00:00 allocation, percentage/fixed-per-unit shelf-life discounts and Prepaid/Deferred quotation-to-PO gates. Update BM01 test targets and ownership references; correct the Report 5 milestone discrepancy. Retain existing effort estimates, assignments and s |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

### The scope reference is SEP490_FA26SE083_R2_Registration.pdf (v1.8), supported by Report 1 v1.7. SRS v1.8 and the related design, test and tracking documents must follow this scope and the confirmed quotation-to-PO workflow. FSCM serves one distributor across multiple warehouses and six human roles: Administrator, Operator, Sales Manager, Warehouse Keeper, Sales and Retailer. Sales create orders; Retailers track orders, accept quotations and confirm actual receipts.

| # | WBS Item | Complexity | Est. Effort (man-days) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | View authorized dashboard (orders, net revenue and sales ranking) | Medium | 8 |  |  |  |
| 2 | Manage user accounts, initial Admin and role/data-scope permissions | Simple | 8 |  |  |  |
| 3 | Manage product, warehouse and delivery master data | Simple | 10 |  |  |  |
| 4 | Manage ordinary promotion rules and order price snapshots | Medium | 10 |  |  |  |
| 5 | Manage retailer profiles, assessment, Category/SKU MLOR and payment terms | Medium | 6 |  |  |  |
| 6 | Capture and review Sales orders before daily cutoff | Medium | 10 |  |  |  |
| 7 | Verify full Prepaid payment after quotation acceptance and before PO release | Medium | 5 |  |  |  |
| 8 | Process complaints and approved financial adjustments | Medium | 6 |  |  |  |
| 9 | Manage Sales groups and territories | Simple | 8 |  |  |  |
| 10 | View Sales-group dashboard (retailers, orders and net revenue) | Simple | 5 |  |  |  |
| 11 | View retailers within assigned Sales territory | Simple | 7 |  |  |  |
| 12 | View and cache product catalog and reference inventory |  | 14 |  |  |  |
| 12.1 | View product catalog and reference inventory | Simple | 5 |  |  |  |
| 12.2 | Cache reference catalog, prices and inventory for offline access | Medium | 9 |  |  |  |
| 13 | Create offline drafts and manually submit after reconnection |  | 22 |  |  |  |
| 13.1 | Create and persist offline Sales order drafts | Simple | 7 |  |  |  |
| 13.2 | Manually submit drafts; revalidate changes and prevent duplicates | Hard | 15 |  |  |  |
| 14 | Track SO, approved quotation, PO lifecycle, prices and notifications | Medium | 10 |  |  |  |
| 15 | Record authorized deferred-payment collection | Medium | 4 |  |  |  |
| 16 | View personal and Sales-group order history | Simple | 4 |  |  |  |
| 17 | View Sales ranking using approved net-revenue rules | Simple | 4 |  |  |  |
| 18 | View Sales dashboard (retailers, orders and net revenue) | Medium | 7 |  |  |  |
| 19 | View Retailer order history, approved prices and payment status | Simple | 4 |  |  |  |
| 20 | Confirm actual warehouse-shipment receipt by QR | Hard | 10 |  |  |  |
| 21 | View Retailer spending and order dashboard | Medium | 6 |  |  |  |
| 22 | Receive scoped order and operational notifications | Medium | 6 |  |  |  |
| 23 | Submit Retailer complaints with quantity and evidence | Medium | 7 |  |  |  |
| 24 | Record and approve goods receipts with batch/QR traceability | Meidum | 14 |  |  |  |
| 25 | View warehouse stock, reservations, locks and expiry status | Simple | 5 |  |  |  |
| 26 | Pick eligible PO warehouse portions and verify full-order readiness | Hard | 19 |  |  |  |
| 27 | Block unusable stock and process authorized write-offs | Simple | 4 |  |  |  |
| 28 | Run idempotent expiry monitoring and operational reminders | Hard | 10 |  |  |  |
| 29 | Commit reservations atomically after Admin approval and revalidation | Hard | 16 |  |  |  |
| 30 | Run 00:00 daily weighted FEFO–MLOR allocation with all-or-nothing orders | Hard | 19 |  |  |  |
| 31 | Calculate promotions and post-allocation batch prices with traceability | Hard | 12 |  |  |  |
| 32 | Maintain operational notifications and audit trail | Medium | 8 |  |  |  |
| 33 | Manage categories and Draft–Published–Inactive product lifecycle | Medium | 4 |  |  |  |
| 34 | Track manual refund obligations, evidence and Admin verification | Medium | 5 |  |  |  |
| 35 | Manage vehicle and delivery-person master data | Simple | 3 |  |  |  |
| 36 | Assign shipment vehicle/person and confirm authorized dispatch | Simple | 3 |  |  |  |
| 37 | Manage percentage/fixed-per-unit shelf-life discounts and pricing snapshots | Medium | 4 |  |  |  |
| 38 | Track deferred receivables, disputed amounts and overdue status | Medium | 3 |  |  |  |
| 39 | Manage auditable loyalty points, gifts and receipt confirmation | Hard | 5 |  |  |  |
| 40 | Manage retailer potential assessment and Sales-area restrictions | Medium | 3 |  |  |  |
| 41 | View best-selling products and net Sales KPI | Medium | 2 |  |  |  |
| 42 | Configure allocation weights and evaluate against strict FEFO | Medium | 3 |  |  |  |
| Total Estimated Effort (man-days) |  |  | 323 |  |  |  |

### Scope includes Category/SKU MLOR, manual offline submission and daily weighted FEFO–MLOR allocation at 00:00 Vietnam time. Only orders received and approved before cutoff enter the run. Admin approves batch prices before reservation; shelf-life discounts are percentage or fixed amount per unit. Retailer quotation acceptance and verified full Prepaid payment or valid Deferred acceptance create the PO and picking lists. All warehouse portions must be fully picked before dispatch. QR receipt, complaint adjustments, verified manual refunds and loyalty remain included. Internal transfers, batch reassignment for later orders, automatic backorders, priority carry-over, COD, route optimization and Retailer-store inventory are excluded.

### 1.2 Project Objectives

| # | Testing Stage | Test Coverage | Defect Criterion | Defect Share | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Reviewing | All critical rules, scope changes and committed workflows reviewed | Recorded | N/A | Track findings and resolution evidence; review is not counted as executable test coverage. |
| 2 | Unit Test | Target ≥70% statement coverage for backend business logic; report measured coverage | Recorded | N/A | Use xUnit/coverlet and flutter_test for allocation, pricing, state transitions, inventory, refunds and points. |
| 3 | Integration Test | 100% of committed critical integration scenarios | Recorded | N/A | Verify UI–API–database, transactions, duplicate requests, cross-scope access and worker retries. |
| 4 | System Test | 100% main workflows; ≥90% overall cases pass; all mandatory main-path tests pass | 0 open Critical/High | N/A | Target ≥50% of committed cases automated in CI. BM01 proposes 119 distinct cases and at least 60 automated; reconcile counts with the final catalogue. Evidence must identify the tested version. |
| 5 | Acceptance Test | 100% main demo scenarios and ≥80% exception demo scenarios pass | 0 open Critical/High | N/A | Defense targets follow Review 2 guidance and the eventual commitment. Test count must meet the agreed commitment; do not present targets as achieved. |

- Milestone Timeliness (%):

  - Target ≥ 95% of baselined milestones completed on or before their agreed due dates, with the Final Defense deadline treated as a fixed commitment.

  - Any critical-path task delayed by more than one working day will trigger an impact assessment and recovery plan. Contingency effort will be allocated according to the impact on core functionality and final delivery.

  - Milestone timeliness = (On-time milestones / Total milestones due) × 100%.

- Allocated Effort (man-days):

  - Planning assumption: 5 members × 15 weeks × 5 project days per week = 375 gross man-days. This is a capacity assumption, not evidence of hours already worked. One man-day represents one planned project working day; hour-based tracking requires an agreed conversion.

  - Reserve 38 man-days (approximately 10%) for project management and coordination. Net delivery capacity is 375 − 38 = 337 man-days; management is not deducted again.

  - Allocate 323 man-days to the functional WBS across requirements, design, implementation and testing, with 14 man-days held as delivery contingency. Therefore, 323 + 14 + 38 = 375 gross man-days. Activity allocation below is another view of the same effort, not additional effort.

| Activity | % Effort | Man-days |
| --- | --- | --- |
| Requirement | 4.00% | 15 |
| Design | 5.33% | 20 |
| Coding | 48.00% | 180 |
| Testing | 28.80% | 108 |
| Project Management | 10.13% | 38 |
| Delivery Contingency | 3.73% | 14 |
| Total | 100% | 375 |

### 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Offline retries create duplicate orders or accept stale conditions. | High | High | Persist drafts and UUIDs; require manual Sales submission and acceptance of changed server conditions; make acceptance idempotent. |
| 2 | Concurrent approvals or stale proposals over-reserve stock. | High | Medium | Revalidate inventory/version and eligibility on approval; reserve complete orders atomically; bounded retries must not silently change approved batches/prices. |
| 3 | Allocation violates MLOR, deadlines or all-or-nothing eligibility. | High | Medium | Test hard filters, server-time priority, shared run pool and deterministic scoring; compare weighted results with strict FEFO on identical eligible data. |
| 4 | Picking, dispatch, receipt or write-off produces inconsistent stock. | High | Medium | Use transactional movement history and QR quantities; require all warehouse portions picked before dispatch; reduce physical stock only on valid dispatch/write-off. |
| 5 | Scheduled jobs fail, overlap or repeat business effects. | High | Medium | Use run locking, idempotency, logged outcomes and controlled retries; recheck expiry/locks at allocation and dispatch. |
| 6 | Integration and scope complexity exceed available capacity. | High | Medium | Review critical integrations early, maintain PIC-based tasks and train on risk areas; use the 14-day delivery buffer through impact review. |
| 7 | Discount/refund calculations lose approved batch-price history. | High | Medium | Store versioned per-batch base, rule, discount and net-price snapshots; cap adjustments by affected net value; require authorized refund evidence and verification. |
| 8 | Duplicate or premature settlement awards incorrect loyalty points. | High | Medium | Award once after full receipt and settlement with no unresolved complaint; retain a ledger for later adjustments and gift receipt. |
| 9 | Conflicting planning documents lead to incompatible implementation. | High | High | Use Registration v1.8 as the scope reference: 00:00 cutoff, percentage/fixed-per-unit shelf-life discounts and no COD. Align SRS, design, tracking and tests with quotation acceptance followed by verified Prepaid or valid Deferred acceptance before PO/picking. |
| 10 | Identity, evidence storage or distance services are unavailable or misconfigured. | High | Medium | Test failure handling and role/warehouse/retailer scope; protect secrets; log failures without inventing successful payments, allocation or receipts. |

## 2. Management Approach

- FSCM uses a Scrum-based iterative approach with a shared backlog and task-level PICs. Each iteration includes design, implementation, review and testing of an integrated business increment. The separate Project Schedule controls iteration dates and milestone commitments.

- The choice of Scrum is justified by the following reasons:

  - Iterative development: Build master data and batch stock, then Sales orders, allocation/price approval, warehouse fulfillment and financial completion.

  - Incremental delivery: Integrate Backend, Portal and Mobile tasks progressively; prototype screens or demonstration data do not establish completed business functionality.

  - Early validation: Review MLOR, all-or-nothing allocation, approval-before-reservation, batch prices, payment authority and loyalty conditions before implementation.

  - Early risk detection: Exercise offline retries, concurrent approvals, multi-warehouse readiness and financial corrections before final integration.

  - Continuous feedback: Review completed work with the team and supervisor, record decisions and assess their impact on requirements, design, tests and estimates.

  - Clear task management: Use Task Tracking PICs for implementation and Project Tracking for planned-versus-actual progress; report blockers and evidence rather than inferring completion.

- Implementation priorities below follow business dependencies; the companion Project Schedule defines the actual sprint placement:

  - Foundation: Authentication and scoped permissions; users, products, warehouses, retailer declarations and Category/SKU MLOR.

  - Core transaction flow: Goods receipt, batch/QR stock, Sales order capture, manual offline submission, daily allocation and Admin price/reservation approval.

  - Fulfillment and finance: Retailer quotation acceptance, verified full Prepaid or valid Deferred acceptance, then PO and picking; complete-order readiness before dispatch, actual receipt, complaints, manual refunds, loyalty, gifts and reports.

  - Integration and stabilization: Run tests throughout development; complete end-to-end and acceptance evidence, fix defects and prepare deployment/documentation. Contingency is conditional and is not an additional committed feature sprint.

### 2.1 Project Process

Use the existing backlog → planning → design/development/testing → review → retrospective cycle shown above. A task is ready for review when its implementation, relevant tests and evidence are available. Completion requires review, successful applicable checks and integration; progress is reflected in the tracking files.

### 2.2 Quality Management

FSCM combines defect prevention, document/code review, unit, integration, system and acceptance testing. Report 5 v1.1 supplies the test strategy and tools; its Test Cases and Test Reports sections still require the catalogue and execution records. BM01 proposes 119 distinct cases: 48 feature, 5 end-to-end, 61 transition and 5 NFR cases, with at least 60 automated. Reconcile the catalogue after rule/state updates; targets are not execution results.

- Defect Prevention

  - Apply naming and coding standards, protect secrets and validate all external input.

  - Define allocation, approved pricing, reservation, full-order readiness, manual submission and financial/loyalty rules before coding.

  - Use transactions, version checks, idempotency and role/data-scope authorization for business writes.

- Reviewing

  - Review pull requests and applicable CI results before merging; AI-assisted changes require the same review and testing.

  - Review requirements and core workflows with the supervisor; retain decisions and link changes to tests and implementation.

  - Review data models, state transitions, batch prices, financial adjustments and permission boundaries.

- Unit Testing

  - Test eligibility, weighted allocation, percentage/fixed-per-unit shelf-life pricing and rounding, inventory, state rules, refunds and loyalty with xUnit and coverage collection.

  - Use flutter_test and suitable UI/form checks for offline persistence, input validation and role navigation; record actual coverage.

- Integration Testing

  - Test Portal/Mobile–REST API–PostgreSQL integration, authentication, evidence storage and asynchronous workers.

  - Verify goods receipt → stock → Sales order → 00:00 allocation/pricing → Admin approval/reservation → Retailer quotation acceptance → verified full Prepaid or valid Deferred acceptance → PO/picking → all warehouse portions ready → dispatch → actual receipt → financial/loyalty completion.

  - Test duplicate requests, cutoff boundaries, transaction rollback, competing reservations, stale approvals, price snapshots, both shelf-life discount types, payment/dispatch gates, unauthorized access and dependency failures. Confirm no batch reassignment for later orders or priority carry-over; award loyalty once only after full receipt, settlement and resolution of complaints.

- System Testing

  - Run end-to-end main and exception scenarios with representative warehouse, order and finance data; retain versioned results and defects.

  - Verify security, stock/financial consistency and offline recovery. Acceptance follows the agreed workflows and quality targets in Section 1.2. Report 5 v1.1 schedules final testing through 25 November 2026, while the companion Project Schedule targets baseline release and verification by 22 November. Reconcile these milestones and identify any post-baseline regression period before committing dates; preserve actual execution dates.

### 2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| FSCM business rules and five integrated workflows | All members | Before implementing the affected flow; refresh after approved changes | Demonstrate the relevant state/stock/payment transitions and explain scope exclusions. |
| Repository setup, CI/CD and safe configuration | Khiết, Hải; other repository contributors as needed | Before first integration/deployment; duration agreed by team | Run the relevant build/tests and explain GitHub → Azure mirror → backend deployment without committing secrets. |
| Flutter offline drafts, SQLite, QR and API integration | Hoàng, Sơn; assigned Mobile PICs | Before relevant mobile tasks; proposed 6–8 hours | Demonstrate persisted offline drafts, manual submission without duplicates and authorized QR handling. |
| Allocation, transactions and approved pricing | Nhân; Backend and integration contributors | Before allocation/approval integration; duration agreed by team | Explain eligibility/scoring, atomic reservation, stale proposal handling and strict-FEFO comparison. |
| Testing, financial corrections and loyalty ledger | All assigned testers; Hải coordinates | Before integration and acceptance testing; duration agreed by team | Execute main/exception cases and explain net-price refund limits, settlement conditions and duplicate protection. |

## 3. Project Deliverables

- The companion Project Schedule remains the source for delivery dates. The following outputs and coordinating PICs are derived from Registration v1.8, Task Tracking and the Review 2 task list; module-level implementation ownership is specified in Section 4.

- Planning and requirements: Registration, Reports 1–3, Project Schedule/Tracking and Review 2 records. Hoàng coordinates Report 2; Khiết Report 1; Sơn SRS; Nhân Project Tracking and Design Brief. Each output requires scope/version consistency and review evidence.

- Design and database: Report 4, architecture, database schema/migrations and diagram sources. Khiết coordinates architecture; Hoàng database design; Hải class diagrams; Sơn activity/sequence work. Verify design and scripts against the agreed requirements before acceptance.

- Software: React Portal, role-based Flutter app, REST services and PostgreSQL scripts. Task Tracking PICs own the relevant components; cross-component acceptance requires an integrated main/exception scenario, not a standalone mock screen.

- Quality and deployment: Report 5 and test results coordinated by Hải; CI evidence, run/setup instructions, demo data and deployment artifacts follow their assigned task PICs. Final acceptance requires committed tests, no open Critical/High defects and reproducible evidence.

- Ownership and baseline follow-up: BM01 Section 8 assigns workflow owners; Section 4 of this plan retains implementation and document PICs. Workflow ownership does not replace task-level responsibility. Reconcile milestone deadlines with the companion schedule and Report 5 before claiming full alignment.

## 4. Responsibility Assignments

D~Do; R~Review; S~Support; I~Informed; <blank>~Not specifically assigned. D follows Task Tracking PICs and document task assignments. Reviewer/support roles must be assigned explicitly; they are not inferred from presenter suggestions. All members support integration of their own work.

| Responsibility | Chiltq6 | Nhanntse184555 | Haiddse190704 | Sonvmse192050 | Hoangtlhse192052 | Khiettnse192015 |
| --- | --- | --- | --- | --- | --- | --- |
| Project planning and tracking; Design Brief | I | D | S | R | R | S |
| Report 1 and architecture/design coordination | I | S | R | R | S | D |
| Report 2 management plan and companion schedule | I | R | R | S | D | S |
| SRS; activity and sequence documentation | I | S | R | D | R | S |
| Report 5 and test-evidence coordination | I | S | D | R | R | S |
| Database design and schema coordination | I | S | R | R | D | S |
| Backend: Portal auth, RBAC, initial Admin, users and product lifecycle | I | S | S | R | R | D |
| Portal: auth, RBAC, users, product lifecycle and QR labels | I | S | R | S | D | R |
| Backend: Mobile login, retailer/MLOR and online order APIs | I | S | D | R | R | S |
| Mobile: login/RBAC, online orders and cached snapshots | I | R | R | D | S | S |
| Portal: categories, warehouses, Sales groups and payment terms | I | R | R | D | S | S |
| Portal/Mobile: retailer declaration, profile and Category/SKU MLOR | I | S | R | S | D | R |
| Backend: offline-draft submission and duplicate protection | I | S | S | R | R | D |
| Mobile: offline drafts, manual submission and order history | I | S | R | S | D | R |
| Backend/Portal: promotions, allocation, proposal/prices and reservation | I | D | S | R | R | S |
| Backend: goods receipt and picking-scan integration | I | S | D | R | R | S |
| Backend: QR labels, expiry locks and write-off | I | S | S | R | R | D |
| Portal: goods receipt, batch status, locks and write-off | I | R | R | D | S | S |
| Backend/Portal/Mobile: picking lists, full-order readiness and dispatch | I | D | S | R | R | S |
| Mobile: picking scans, receipt QR and batch-price details | I | S | R | D | S | R |
| Mobile: QR lookup, Retailer order/payment/debt views | I | S | R | S | D | R |
| Backend: shipment coordination, prepaid/deferred finance and refunds | I | S | S | R | R | D |
| Portal: prepaid/deferred finance and manual refund evidence | I | S | R | D | S | R |
| Backend: collection API and Retailer financial views | I | S | D | R | R | S |
| Portal: collection, delivery assignments, ranking and best sellers | I | S | R | S | D | R |
| Backend/Portal/Mobile: complaints, loyalty and gift redemption | I | D | S | R | R | S |
| Backend: KPI, best sellers and in-app notifications | I | S | D | R | R | S |
| Portal/Mobile: in-app notifications and integration tests | I | S | R | S | D | R |
| Backend: push and overdue jobs; demo seed data | I | S | S | R | R | D |
| Mobile: push, Sales KPI and debt tracking | I | S | R | D | S | R |
| Backend: integration verification, bug fixes and final deployment | I | S | D | R | R | S |
| Portal/Mobile: final fixes and build delivery | I | S | R | D | S | R |
| Cross-component review, acceptance and defense preparation | I | D | D | D | D | D |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Supervisor review | Supervisor; leader and relevant PICs | - Review scope/design, blockers and milestone readiness; record decisions | At agreed appointments and milestone reviews; confirm recurring cadence | Meeting/online channel agreed with supervisor; retain meeting minutes in Drive |
| Team coordination | All members; leader coordinates | - Review tasks, dependencies, blockers and integration evidence | At iteration planning/review and regular team check-ins; cadence agreed by team | Team channels (Discord/Teams/Meet as used); Task Tracking/Azure DevOps; recorded actions |
| Code and integration review | Author and assigned reviewer; affected PICs | - Review changes, CI failures and cross-component contracts | For each pull request and affected integration | GitHub PR/Issues and CI links; mirror/deployment logs where relevant |
| Baseline or risk escalation | Leader, affected PICs; supervisor when required | - Resolve conflicting rules, assess impact and record owner/deadline | When scope, acceptance, effort or critical-path commitments change | Decision/change log linked to affected reports and tracking |

## 6. Configuration Management

Control requirements, documents, source code, tests and deployment artifacts as linked baselines. Record changes and their impact across Reports 1–5, the two tracking workbooks and the companion Project Schedule; do not assume one revised file automatically updates the others.

### 6.1 Document Management

- The team uses Google Drive as the primary platform for storing and managing project documents. All project-related documents are organized in shared folders that can be accessed by all team members.

- Document versions are managed using the following rules:

  - Include a filename version and Record of Changes; this document is Report2_Project_Management_Plan_v1.5.docx.

  - For material changes, retain the previous version and record the scope, estimate, responsibility and test impact. Reassess WBS effort when workflow or test scope changes; retain the current 323 man-day estimate and 375 man-day capacity until an impact estimate is approved.

  - Each document contains a Record of Changes table to record:

    - Date of change

    - Change type: Added / Modified / Deleted

    - Person in charge

    - Description of the change

  - Retain historical and submitted documents in Drive; identify working, reviewed and approved baselines explicitly.

  - Before using a revised baseline, align Registration, Reports 1–5, WBS/tracking and the companion schedule. Record unresolved differences with an owner and planned resolution.

  - Scope control: Registration v1.8 governs the 00:00 Vietnam-time daily run, percentage/fixed-per-unit shelf-life discounts and Prepaid/Deferred payments without COD. Report 1 v1.7 and this plan adopt quotation acceptance followed by verified full Prepaid or valid Deferred acceptance before PO/picking. Align SRS v1.8, SDD v1.8, Report 5 v1.1, BM01 and tracking with these rules. BM01 already contains an Ownership Map; reconcile the 22/25 November test milestones. Record later revisions and review decisions separately; the Registration reviewer-decision table is not yet completed.

### 6.2 Source Code Management

- Use GitHub Organization GFA26SE63 for FSCM-Backend, FSCM-Frontend and FSCM-Mobile. GitHub is the normal development/PR remote; mirror workflows copy pushed branches to matching Azure DevOps repositories. TEAM_SETUP documents the configured pipelines; verify run evidence for each delivery.

- The source code is managed using the following practices:

  - Keep application changes in their owning repositories; cross-system documentation is managed separately.

  - Track traceable commits and link changes to task/issue IDs, requirements and tests where applicable.

  - Develop changes on branches and submit pull requests for assigned review before merging to main.

  - Review applicable CI results: Backend restore/build/tests; Frontend dependency install/lint/build; Mobile format/analyze/tests. A frontend build does not establish automated functional-test coverage.

  - Use clear commit messages and record reviewed changes; never commit passwords, keys, connection strings or local environment files.

  - Use reviewed main for stable integration. The backend mirror main triggers the Azure Pipeline build/test/package/deploy stages to Azure App Service; Frontend/Mobile CD is not established by the setup guide.

  - Identify review/defense submissions with an agreed tag (review-2 for Review 2), linked tests, schema scripts and documentation. Record the deployed commit/artifact; rollback must use a verified prior artifact with database compatibility checked.

  - Manage repository access through authorized accounts. Separate development configuration from deployed environments; staging/production topology and recovery procedures require explicit verification before being reported as complete.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | React/TypeScript (Portal), Flutter (Mobile), ASP.NET Core REST API (.NET 10). Business GraphQL capability is not assumed from a status-only endpoint. |
| Database | Azure Database for PostgreSQL; SQLite for Mobile cached reference data and offline drafts. Confirm PostgreSQL engine version in the actual test environment. |
| IDEs/Editors | Visual Studio, Visual Studio Code, Android Studio and team-selected editors/AI assistants. Record actual AI tools/models and phases used; do not infer models from editor names. |
| Diagramming | Draw.io and Mermaid; retain editable diagram sources and versions. |
| Documentation | Microsoft Office, Google Docs/Sheets/Slides and shared Google Drive; versioned Reports 1–5 and tracking workbooks. |
| Version Control | GitHub Organization GFA26SE63 with three application repositories; GitHub-to-Azure DevOps mirroring. Drive stores document baselines. |
| Deployment server | Vercel for planned Portal hosting. TEAM_SETUP documents Backend deployment to Azure App Service through Azure Pipelines. Worker hosting and separate staging/production configuration require confirmation. |
| Project management | Task Tracking Scope V10 for detailed PIC/status; Report3_Project_Tracking for WBS progress; Azure DevOps and GitHub Issues as applicable. |
| CI and test tools | GitHub Actions; Azure Pipelines for backend CD; xUnit, coverlet.collector, flutter_test, TestServer and Swagger UI. Setup records Node.js 22 and Flutter 3.44.0; verify installed versions for each run. |
| Identity, storage and operations | Registration proposes Microsoft Entra ID, Azure Key Vault, Blob Storage and Azure Monitor; scheduled worker/optional Azure Functions. Distinguish proposed services from verified deployments; confirm mobile authentication and distance-provider integration. |