FA26SE083 — PROJECT SCHEDULE

| Name | Duration | Start | Finish | Predecessors | Resource Names | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 1 FA26SE083 — FSCM Project Schedule | To Week 15 | 04/08/ 2026 | Week 15 TBC |  | All members | 167 tasks: S1 19 Oct–1 Nov (64), S2 2–15 Nov (68), S3 16–22 Nov (35). Review 2: 29 Oct. Councils 1.1/1.2: academic Weeks 14/15, dates TBC. S4 only if Council 2 is required (~Week 19). Version 1.5: revised cutoff, payment/loyalty rules, test evidence and release/stabilization gates; submission-deadline reconciliation remains pending. |
| 2 Project Start | 0 days | 04/08/ 2026 | 04/08/ 2026 |  | All members | Start of the original four-week preparation period. |
| 3 Initiation & Early Preparation (Stage 1) | 28 days | 04/08/ 2026 | 31/08/ 2026 | 2 | All members | Preparation weeks 1–4, before the official project term. |
| 4 Kick-off, role assignment and domain research | 14 days | 04/08/ 2026 | 17/08/ 2026 | 2 | All members; Nhan, Khiet | Deliverables: Team Charter, responsibility allocation and Domain Research Note. |
| 5 Technical spikes: concurrency, offline queue and Redis | 21 days | 04/08/ 2026 | 24/08/ 2026 | 4SS | Nhan, Son, Khiet | Deliverables: experimental repository and feasibility findings; retained from the original preparation plan. |
| 6 Draft scope, business analysis, ERD and architecture | 21 days | 11/08/ 2026 | 31/08/ 2026 | 4SS | All members | Deliverables: draft scope and MoSCoW priorities, business analysis, ERD and architecture. |
| 7 Set up repositories, CI, task board and wireframes | 14 days | 18/08/ 2026 | 31/08/ 2026 | 5SS | Nhan, Son; Hai, Hoang | Deliverables: buildable base code, Azure Board, Portal and Mobile wireframes. |
| 8 Planning & Requirements (Stage 2) | 21 days | 01/09/ 2026 | 21/09/ 2026 | 6;7 | All members | Existing planning dates retained. Roadmap: Reports 1/2/3 overview due Weeks 1/2/3; submit registration, Reports 1–3 and Project Tracking for Review 1 by end Week 3. |
| 9 Finalize Scope Statement, MoSCoW and MVP | 14 days | 01/09/ 2026 | 14/09/ 2026 | 6 | All members | Agree scope and priorities for Review 1. Address feedback and obtain supervisor confirmation of updated registration by end Week 6; freeze it as the Council 1.1 baseline. |
| 10 Business analysis v1.0 and preliminary API specification | 21 days | 01/09/ 2026 | 21/09/ 2026 | 9SS | Khiet, Hai; Nhan | Deliverables: business processes, use cases and preliminary API contracts. |
| 11 Architecture, ERD and Data Dictionary | 14 days | 01/09/ 2026 | 14/09/ 2026 | 6 | Nhan | Deliverables: Architecture Diagram, batch-level ERD and Data Dictionary. |
| 12 Database migrations, base code and sprint planning | 14 days | 08/09/ 2026 | 21/09/ 2026 | 7 | Nhan, Son; All members | Deliverables: migrations from an empty database, repository/CI setup, schedule and initial assignments. |
| 13 Review 1 — Feasibility, requirements & scope | 0 days | 02/10/ 2026 | 02/10/ 2026 | 9;10;11;12 | All members | Review held on 2 Oct 2026: feasibility, requirements and scope. Retain minutes and resolve feedback. Roadmap: dossier due end Week 3 and ≥2 working days beforehand; supervisor confirms revised registration by end Week 6. |
| 14 Software Design (Stage 3) | 50 days | 08/09/ 2026 | 27/10/ 2026 | 11SS | Nhan, Khiet, Hai | Complete the core Review 2 reports and design documents by 27 Oct. Run the AI-assisted consistency review and make supplementary corrections on 28 Oct before Review 2 on 29 Oct. Preserve the completed baseline and record subsequent revisions. |
| 15 Refine business processes, use cases and SRS | 50 days | 08/09/ 2026 | 27/10/ 2026 | 10SS | Khiet, Hai | Report 3: SRS and business flows for daily allocation at 00:00 in Asia/Ho_Chi_Minh, goods/price approval, reservation, manual offline submission and batch pricing. Both server acceptance and order approval must be strictly before cutoff; either timestamp at/after cutoff means the next run. Submit by the confirmed Review 2 deadline; retain the existing 27 Oct target until resolved. |
| 16 Finalize module design, sequences and ERD | 9 days | 19/10/ 2026 | 27/10/ 2026 | 11;13 | Nhan | Report 4: architecture, detailed design, sequences, ERD and migrations aligned with Scope V10; no internal transfers or batch reassignment. Submit by the confirmed Review 2 deadline; existing target: 27 Oct. Record later supplementary revisions separately and retain original submission/version history. |
| 17 API contracts, test plan & Iteration 1 package | 9 days | 19/10/ 2026 | 27/10/ 2026 | 10;13 | Nhan, Khiet; All members | Prepare API contracts, the Report 5 test plan and the available Iteration 1 code/database package by 27 Oct. Run the review prompt and address identified documentation gaps on 28 Oct; retain the review output, responses and revised versions. S1 continues to 1 Nov. |

| Name | Duration | Start | Finish | Predecessors | Resource Names | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 18 Implementation (Stage 4) | 35 days | 19/10/ 2026 | 22/11/ 2026 | 13 | All members | Tracker baseline unchanged: S1/S2/S3 = 64/68/35 tasks; Backend 82, Portal 51, Mobile 34. Iterations are delivery gates, not assumed 1:1 with sprints. Package 1 precedes Review 2; Package 2 is due Week 11; full package is due Week 13. |
| 19 Sprint 1 — Foundation, orders & inventory | 14 days | 19/10/ 2026 | 01/11/ 2026 | 13;16SS;17SS | All members | 64 tasks: BE 31, Portal 21, Mobile 12. PIC totals: Nhan 8, Khiet 10, Hai 17, Son 13, Hoang 16. Deliver working Iteration 1 code before Review 2 submission; remaining S1 tasks continue to 1 Nov. |
| 20 Authentication, users and master data | 14 days | 19/10/ 2026 | 01/11/ 2026 | 19SS | Khiet, Hai, Son, Hoang | F08–F23: Portal/Mobile login, six-role access, seeded Admin, users, profiles, products, warehouses, Sales regions, two-tab retailer profiles, MLOR Category/SKU and credit terms. |
| 21 Promotions, online orders and pre-cutoff approval | 14 days | 19/10/ 2026 | 01/11/ 2026 | 19SS;20SS | Nhan, Hai, Son, Hoang | F24–F28, F32, F36–F37: ordinary promotions, indicative prices, Sales orders, region checks, order lists/details and approval before cutoff. No batch selection or reservation at order intake. |
| 22 Receipts, QR labels, ETA and payments | 14 days | 19/10/ 2026 | 01/11/ 2026 | 19SS;20SS | All members | F39–F42, F45, F54–F56, F63: goods receipts/batches, QR printing/lookup, expiry monitoring, transport rules, distances, shared ETA and prepaid/deferred payment handling. Prepayment follows final allocation/price approval and must be fully verified before dispatch. Deferred payment follows approved retailer credit terms. Align F63-BE/FE/MB document descriptions and authorized payment roles with this rule. |
| 23 Sprint 2 — Allocation & end-to-end business flow | 14 days | 02/11/ 2026 | 15/11/ 2026 | 19 | All members | 68 tasks: BE 34, Portal 20, Mobile 14. PIC: Nhan 36, Khiet 9, Hai 6, Son 9, Hoang 8. Iteration 2: Weeks 10–11; Software Package 2 and Reports 3–5 updates due Week 11. Verify the academic-week gate; retain tracker sprint dates. |
| 24 Manual offline submission, allocation and pricing | 14 days | 02/11/ 2026 | 15/11/ 2026 | 23SS;21;22 | All members | F29–F31, F33, F35, F46, F85, F87–F91, F98: manual offline submission; daily allocation at 00:00, Asia/Ho_Chi_Minh. Server acceptance and approval must both be strictly before cutoff; at/after cutoff waits for the next run. Apply MLOR/ETA filters, weighted scoring and percentage/fixed batch discounts after selection. Admin approves goods/prices before atomic reserve. No automatic shortage carry-over; new orders receive new timestamps and no retained priority. |
| 25 Picking, dispatch, receipt and receivables | 14 days | 02/11/ 2026 | 15/11/ 2026 | 23SS;24SS | All members | F43–F44, F57–F58, F60–F61, F64–F65, F92–F93, F96, F100–F101: stock lock, warehouse shipments, scans, whole-order readiness, dispatch, actual receipt, receivables, single settlement and verified manual refunds. |
| 26 Loyalty, gift redemption, KPI and rankings | 14 days | 02/11/ 2026 | 15/11/ 2026 | 23SS;25SS | All members | F69–F76, F78: loyalty program, ledger, gifts/redemption, KPI/ranking and best sellers. Award points once only after full receipt, full payment and no unresolved complaint. Later financial adjustments create traceable correcting point-ledger entries, preserving the original award. Nhan owns loyalty; Hai/Khiet Backend and Son/Hoang Portal own KPI/rankings per tracker. |
| 27 Review 2 — SRS, design & required features | 0 days | 29/10/ 2026 | 29/10/ 2026 | 14;15;16;17;19SS | All members | Review 2 session: 29 Oct 2026. Complete the core report set by 27 Oct; conduct AI-assisted checking and supplementary revisions on 28 Oct. Record reviewed versions, outstanding gaps, feedback, owners and follow-up dates. |
| 28 Sprint 3 — Completion, verification & handover | 7 days | 16/11/ 2026 | 22/11/ 2026 | 23 | All members | 35 tasks: BE 17, Portal 10, Mobile 8. PIC: Nhan 11, Khiet 7, Hai 4, Son 8, Hoang 5. Complete planned S3 implementation, baseline verification and deployment by 22 Nov. Iteration 3: Weeks 12–13. Post-release regression/stabilization runs 23–25 Nov under Stage 6, with separate evidence; finalize Council 1.1 readiness. |
| 29 Allocation controls, write-off and complaints | 7 days | 16/11/ 2026 | 22/11/ 2026 | 28SS;25 | Nhan, Khiet, Son | F38, F47, F59, F62, F94–F95: weight/radius settings, expiry write-off, delivery-cost estimate, complaints, cancellation after reserve before picking, run closure/report. No internal transfers or batch swaps. |
| 30 Overdue balances, dashboards and notifications | 7 days | 16/11/ 2026 | 22/11/ 2026 | 28SS;26 | Khiet, Hai, Son, Hoang | F66–F68, F77, F79–F81: overdue job, Sales/Retailer receivables, Mobile KPI/ranking, Admin dashboard, in-app and push notifications. Preserve the tracker PIC for each platform task. |
| 31 Allocation scenarios and FEFO comparison | 7 days | 16/11/ 2026 | 22/11/ 2026 | 28SS;24 | Nhan | F97, F99 outputs: versioned cases, datasets and results for 00:00 Asia/Ho_Chi_Minh cutoff; strictly-before acceptance/approval and exact-cutoff exclusion; MLOR/ETA; shortage rollback; percentage/fixed discounts after batch selection; approved price snapshots; atomic reserve/concurrency; no batch reassignment for later orders or retained priority; full-order readiness. Compare weighted greedy with strict FEFO on identical data, eligibility and order priority. |
| 32 Verification — Sprint 3 (Stage 5) | 7 days | 16/11/ 2026 | 22/11/ 2026 | 28SS;25;26 | Khiet, Hai, Son, Hoang | F82–F84 remain in S3: demo data, integration/permission tests, fixes and baseline deployment by 22 Nov. Prepare baseline Report 5 results by 22 Nov; append regression/stabilization results from 23–25 Nov under Stage 6. By Week 13 finalize Full Software Package and draft Report 6; submit Council 1.1 dossier by end Week 13 and ≥2 working days before the session. |
| 33 Internal progress demo & mock defense | 0 days | 16/11/ 2026 | 16/11/ 2026 | 23;28SS | All members | Internal checkpoint only; the roadmap has two official reviews. Demo S1/S2 flows and available S3 work on 16 Nov. Track defects and close S3 by 22 Nov; this checkpoint does not replace Council 1.1 or Council 1.2. |
| 34 Seed demo data and test end-to-end workflows | 7 days | 16/11/ 2026 | 22/11/ 2026 | 32SS;31SS | Khiet, Hai, Hoang | F82–F83 outputs: reproducible seed data, E2E cases, expected/actual results, version and evidence. Khiet seeds; Hai tests Backend; Hoang Portal/Mobile. Cover manual submission → strictly-before acceptance/approval → 00:00 allocation with fixed/percentage discounts → Admin approval/reserve → full-order readiness → verified prepaid gate or approved deferred terms → dispatch/actual receipt. Include missing receipt, complaints, net-price adjustments/refunds and points awarded once after full receipt/payment with no unresolved complaint; later adjustments correct the ledger. |
| 35 Transition & Council preparation (Stage 6) | To Week 15 | 17/11/ 2026 | Week 15 TBC | 33 | All members | Baseline release: 22 Nov. Conduct post-release regression and stabilization on 23–25 Nov; record defects, retest results and any corrective release separately. Continue documents/demo through Councils 1.1/1.2 in Weeks 14/15. Align Report 5 §3.3 to these two gates. S4 remains conditional on a non-pass and Council 2. |
| 36 Fix defects and deploy the final release | 7 days | 16/11/ 2026 | 22/11/ 2026 | 34SS | Hai, Son | F84: Hai handles Backend fixes, migrations/deployment; Son handles Portal/Vercel and Mobile fixes/demo APK. Deploy baseline release by 22 Nov. Regression/stabilization and any corrective deployment continue 23–25 Nov under Stage 6 with separate version/test evidence. S4 is reserved for a required Council 2. |
| 37 Reports, user guides & defense preparation | To Week 15 | 17/11/ 2026 | Week 15 TBC | 33;35SS | All members; Hai, Hoang; Nhan, Son | End Week 13: Full Software Package, baseline Report 5 results by 22 Nov, draft Report 6 and Council 1.1 dossier; append regression/stabilization evidence through 25 Nov. Complete Reports 1–6 for 1.1. If passed, finalize Report 7, slides, demo, README, guides, Q&A and rehearsal for 1.2. Submit ≥2 working days before each council; dates TBC. |
| 38 Council 1.1 — Defense eligibility assessment | 0 days | Week 14 TBC | Week 14 TBC | 32;34;36;37SS | All members | Three-member council assesses product against frozen registration, required features, SRS and Design. Submit full package/demo, Reports 1–6, frozen registration and Review 1–2 minutes by end Week 13 and ≥2 working days beforehand. Pass → Council 1.2; non-pass → conditional S4 / Council 2. |
| 39 Council 1.2 — Final defense | 0 days | Week 15 TBC | Week 15 TBC | 38;37 | All members | After passing Council 1.1: present and defend the product. Submit Report 7, slides, final source/database scripts, test evidence and Project Tracking ≥2 working days beforehand. Pass → complete; non-pass → S4/Council 2. Date TBC. |
| 40 Sprint 4 — Conditional Council 2 contingency | TBC | After non-pass | Before Council 2 | 38 or 39 (non-pass) | All members | Only if Council 1.1 or 1.2 is not passed: fix issues from council minutes, retest, redeploy and prepare an itemized response. No baseline feature tasks. Dates follow the council decision and Council 2 timetable (~Week 19, next semester). |
| 41 Council 2 — Conditional reassessment | 0 days | ~Week 19 TBC | ~Week 19 TBC | 40 | All members | Conditional reassessment approximately 4 weeks after Week 15, next semester. Submit updated product/documents and itemized responses ≥2 working days beforehand. Exact group timetable TBC. |