CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

– Ho Chi Minh City, September 2026 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	4

1.3 Project Risks	4

2. Management Approach	5

2.1 Project Process	5

2.2 Quality Management	5

2.3 Training Plan	5

3. Project Deliverables	5

4. Responsibility Assignments	5

5. Project Communications	6

6. Configuration Management	6

6.1 Document Management	6

6.2 Source Code Management	6

6.3 Tools & Infrastructures	6

# I. Record of Changes

| Date | A, M, D * | In charge | Change Description |
| --- | --- | --- | --- |
| 15/09/2026 | A | Tran Ngoc Khiet | Version 1.0 Add: - 1.1 Scope & Estimation - 1.2 Project Objectives |
| 23/09/2026 | A, M | Tran Ngoc Khiet | Version 1.1 Modified: - 1.1 Scope & Estimation: Update functions based on new project details - 1.2 Project Objectives: Add testing plan and project man-days allocation Add: - 1.3 Project Risks - 2. Management Approach - 2.1 Project Process - 2.2 Quality Management - 4. Responsibility Assignments - 5. Project Communications - 6. Configuration Management - 6.1 Document Management - 6.2 Source Code Management - 6.3 Tools & Infrastructures |
| 27/09/2026 | A, M, D | Tran Ngoc Khiet | Version 1.2 Add: - 2.3 Training Plan - 3. Project Deliverables (file) Modified: - 1.1 Scope & Estimation: Update new scope base on Coreflow_v1.1.xlsx - 4. Responsibility Assignments: Update new responsibility and assign to members Deleted - 1.1 Scope & Estimation: Delete old scope features |
| 27/09/2026 | A, M | Truong Le Huy Hoang | Revised role responsibilities and corrected spelling errors. Add training plan area Flutter |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| Admin |  |  |  |
| 1 | View dashboard (order, revenue, sale leaderboard) | Medium | 8 |
| 2 | Manage user account |  | 8 |
| 2.1 | CRUD on account | Simple | 4 |
| 2.2 | Authorized account (log in / log out), change account status | Simple | 4 |
| 3 | Manage metadata |  | 10 |
| 3.1 | Manage product/SKU (price, category, expiry) | Simple | 5 |
| 3.2 | Manage warehouse (location, max serving data, coordinate) | Simple | 5 |
| 4 | Manage promotion rule | Medium | 10 |
| 5 | Manage retailer data and policy | Simple | 6 |
| Operator |  |  |  |
| 6 | Process purchase order |  | 10 |
| 6.1 | Approve or decline order (with decline reason) | Simple | 4 |
| 6.2 | Update order life-cycle status | Medium | 6 |
| 7 | Confirm order payment with QR code / bank transfer | Simple | 5 |
| 8 | Process report for damaged goods or discrepancy in order amount and actual delivery amount | Simple | 6 |
| Sale manager |  |  |  |
| 9 | Manage sale group |  | 8 |
| 9.1 | CRUD on sale group | Simple | 4 |
| 9.2 | Assign sale/area/retailer to sale group | Simple | 4 |
| 10 | View sale group dashboard (order, retailer, revenue) | Simple | 5 |
| Sale |  |  |  |
| 11 | View sale area and list of retailer in their sale group |  | 7 |
| 11.1 | View sale group information | Simple | 2 |
| 11.2 | View sale area | Simple | 2 |
| 1.3 | View list of active assigned retailer | Simple | 3 |
| 12 | View product catalog and inventory balance (cache data for offline access) |  | 14 |
| 12.1 | View product catalog and inventory balance | Simple | 5 |
| 12.2 | Cache product catalog and inventory balance for offline access | Medium | 9 |
| 13 | Create order when offline, auto sync when online |  | 22 |
| 13.1 | Create purchase order (with or without internet) | Simple | 7 |
| 13.2 | Sync purchase order when internet connection available | Hard | 15 |
| 14 | Tracking order life-cycle status and receive notification |  | 10 |
| 14.1 | View purchase order life-cycle status | Simple | 4 |
| 14.2 | Retrieve live notification about the status | Medium | 6 |
| 15 | Confirm pay in cash purchase order | Simple | 4 |
| 16 | View order history (personal and sale group) | Simple | 4 |
| 17 | View sale leaderboard | Simple | 4 |
| 18 | View sale dashboard (retailer, order, revenue) | Medium | 7 |
| Retailer |  |  |  |
| 19 | View order detail and order history | Simple | 4 |
| 20 | Scan QR code to confirm delivery order | Hard | 10 |
| 21 | View dashboard (order and spending) | Medium | 6 |
| 22 | Receive order status and notification | Medium | 6 |
| 23 | File report if any damaged goods or discrepancy between order amount and actual delivery amount | Medium | 7 |
| Warehouse Keeper |  |  |  |
| 24 | Tracking goods receive note (GRN) life-cycle status and receive notification |  | 14 |
| 24.1 | Create goods receive note | Simple | 6 |
| 24.2 | Retrieve live notification about the status | Medium | 5 |
| 24.3 | View goods receive history | Simple | 3 |
| 25 | View inventory balance and life-cycle status (Normal/Near-date/Expired) | Simple | 5 |
| 26 | Process picking list to export batches |  | 19 |
| 26.1 | Receive notification when a picking list is assigned | Medium | 4 |
| 26.2 | Scan batch’s QR to update inventory | Hard | 10 |
| 26.3 | View and update picking list | Simple | 5 |
| 27 | Block expiry batches | Simple | 4 |
| System Automation Services and overview function |  |  |  |
| 28 | Cronjob to track batches, block expiry batches, mark near-date batches | Hard | 10 |
| 29 | Handle concurrent allocation using optimistic locking and automatic batch fallback | Hard | 16 |
| 30 | Run multi-warehouse batch picking for each SKU when receive order | Hard | 18 |
| 31 | Pick promotion when create purchase order | Hard | 12 |
| 32 | Notify when status change with audit trail | Medium | 8 |
| Total Estimated Effort (man-days) |  |  | 287 |

### 1.2 Project Objectives

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Reviewing | ≥ 95% of planned documents; 100% of critical business rules and core flows | ≤ 10 | 25% | Review FEFO rules, inventory updates, approval permissions, offline synchronization, and UI flows before implementation. |
| 2 | Unit Test | ≥ 70% statement coverage of backend business-logic modules | ≤ 16 | 40% | Cover batch eligibility, FEFO ordering, quantity validation, reservation calculations, and order state transitions. |
| 3 | Integration Test | 100% of identified critical API and service integration scenarios | ≤ 8 | 20% | Test the complete flow: goods receipt approval → order synchronization → order approval → FEFO reservation → goods issue → receipt reconciliation. |
| 4 | System Test | ≥ 95% of agreed user stories; 100% of Must-have user stories | ≤ 4 | 10% | Validate the system with representative users or designated reviewers. All mandatory acceptance scenarios must pass before delivery. |
| 5 | Acceptance Test | 100% of agreed core business acceptance scenarios | ≤ 2 | 5% | Initial estimates of unique defects first detected at each stage; not allowable unresolved defects. |

- Milestone Timeliness (%):

  - Target ≥ 95% of baselined milestones completed on or before their agreed due dates, with the Final Defense deadline treated as a fixed commitment.

  - Any critical-path task delayed by more than one working day will trigger an impact assessment and recovery plan. Contingency effort will be allocated according to the impact on core functionality and final delivery.

  - Milestone timeliness = (On-time milestones / Total milestones due) × 100%.

- Allocated Effort (man-days):

  - The team consists of 5 members working 5 days per week for 15 weeks. The remaining two days per week are reserved for the politics course, project review presentations, and rest. Team meetings and management occupy 10% of total project working time.

  - Net capacity = 5 members × 15 weeks × 5 days/week × 90% = 337.5 man-days, rounded down to 337 man-days for planning.

  - Of this capacity, 287 man-days are allocated to planned activities, and 50 man-days (~15%) are reserved for unexpected defects, integration difficulties, and additional rework.

| Activity | % Effort | Man-days |
| --- | --- | --- |
| Requirement | 4.45% | 15 |
| Design | 4.45% | 15 |
| Coding | 51.34% | 173 |
| Testing | 29.67% | 100 |
| Project Management | 10.09% | 34 |
| Total | 100% | 337 |

### 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Offline order synchronization may cause duplicate or conflicting data. | High | High | Use local sync queue, idempotency key, and revalidate inventory on server before confirming. |
| 2 | Concurrent orders may reserve the same inventory batch. | High | Medium | Apply optimistic locking, transactions, and automatically retry with the next eligible batch. |
| 3 | Incorrect FEFO/MLOR allocation may select unsuitable batches. | High | Medium | Isolate allocation logic, add unit tests, and validate FEFO, MLOR, partial allocation, and multi-warehouse cases. |
| 4 | Inventory balance may become inconsistent across receiving, delivery, reservation, and write-off operations. | High | Medium | Centralize inventory updates, use transactions, and maintain batch-level inventory movement history. |
| 5 | Batch expiration tracking job may fail or update statuses incorrectly. | High | Medium | Make cronjobs idempotent, log executions, support retries, and recheck expiry during allocation/export. |
| 6 | The team may underestimate the complexity of offline sync, concurrency, and inventory logic. | High | Medium | Build critical prototypes early, conduct technical training, and reserve buffer effort for complex modules. |

## 2. Management Approach

- The project applies an Agile Scrum-based development approach to manage and implement the FSCM system. Development is divided into short iterations so that the team can progressively implement, test, review, and improve each core business flow.

- The choice of Scrum is justified by the following reasons:

  - Iterative development: Core workflows such as order creation, GRN/GDN, inventory management, FEFO allocation, and write-off can be developed and validated step by step.

  - Incremental delivery: Basic CRUD and inventory functions can be completed first before implementing more complex functions such as offline synchronization and optimistic locking.

  - Early validation of business rules: FEFO, MLOR, batch eligibility, reservation, and inventory updates can be reviewed and tested after each sprint.

  - Early risk detection: Technical risks such as synchronization conflicts, concurrent reservations, and incorrect inventory balances can be discovered before final integration.

  - Continuous feedback: Sprint reviews allow the team and supervisor to evaluate completed features and adjust requirements when necessary.

  - Clear task management: Sprint goals and assigned tasks help track each member's progress and maintain project schedule.

- A sensible implementation sequence for FSCM would be:

  - Sprint 1: Project setup, authentication, users, SKU, warehouse and basic metadata

  - Sprint 2: Inventory, Batch/Lot and Goods Receipt

  - Sprint 3: Purchase order, FEFO/MLOR allocation and reservation

  - Sprint 4: Picking list, GDN and inventory deduction

  - Sprint 5: Offline order creation and synchronization

  - Sprint 6: Write-off, notifications, dashboard and system automation

  - Final Sprint: Integration testing, system testing, bug fixing and documentation

### 2.1 Project Process

### 2.2 Quality Management

To achieve the project quality objectives, FSCM applies a quality management approach combining defect prevention, reviewing, unit testing, integration testing, and system testing throughout development.

- Defect Prevention

  - Apply coding standards and naming conventions.

  - Clearly define FEFO/MLOR, reservation, inventory, and offline synchronization rules.

  - Apply input validation, database transactions, and optimistic locking.

- Reviewing

  - Conduct code reviews before merging.

  - Review requirements and core workflows with the supervisor.

  - Review database, FEFO/MLOR logic, UI/UX, and inventory-related processes.

- Unit Testing

  - Test FEFO/MLOR, inventory calculations, reservation, batch status, write-off, and offline synchronization logic.

  - Test key frontend/mobile forms and validations.

- Integration Testing

  - Test frontend/mobile–backend–database integration.

  - Verify Order → Allocation → Picking → GDN and GRN → Inventory flows.

  - Test API responses, transactions, notifications, and concurrent reservations.

- System Testing

  - Conduct end-to-end tests based on real warehouse and distribution scenarios.

  - Verify stability, performance, security, inventory consistency, and offline operation.

### 2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| FMCG supply chain | All members | First 6 weeks of the project | Understand main concept of the supply chain |
| Azure | Khiết, Hải | First 6 weeks of the project | Enough to use all the Azure’s services listed in the Tools & Infrastructures |
| Flutter offline-first development: SQLite caching, order queue and synchronization | Hoàng, Sơn | One week before mobile implementation; 6–8 hours | Waived if the participant demonstrates a working prototype that stores an order offline and synchronizes it without creating duplicates. |

## 3. Project Deliverables

- File FPTUCP_Report2_Project_Schedule.docx

## 4. Responsibility Assignments

D~Do; R~Review; S~Support; I~Informed; <blank>- Omitted

| Responsibility | Chiltq6 | Nhanntse184555 | Haiddse190704 | Sonvmse192050 | Hoangtlhse192052 | Khiettnse192015 |
| --- | --- | --- | --- | --- | --- | --- |
| Project Planning, Tracking & Sprint Management | I | D | R | R | R | D |
| Prepare Project Introduction, SRS & Risk Management Documents | I | D | R | R | S | D |
| System Architecture Design | I | D | R | R | S | D |
| Database Design – ERD & Schema | I | S | R | R | R | D |
| UI/UX Design | I | D | D | D | R | R |
| Authentication, Authorization & User Account Management | I | S | D | R | R | D |
| Master Data Management – Product/SKU, Warehouse, Retailer & Policy | I | D | D | S | R | D |
| Sales Group, Sales Area & Retailer Assignment Management | I | S | D | R | R | D |
| Promotion Rule & Promotion Selection Logic Implementation | I | S | D | R | R | D |
| Product Catalog, Inventory View & Offline Cache Implementation | I | S | D | S | S | D |
| Purchase Order, Order Approval & Order Life-cycle Management | I | S | D | R | R | D |
| Offline Order Creation, Synchronization & Conflict Handling | I | D | D | S | S | D |
| Payment Confirmation – QR/Bank Transfer & Cash | I | R | S | R | R | D |
| Dashboard, Order History & Sales Leaderboard Implementation | I | R | D | R | R | D |
| Retailer Order Receipt, QR Confirmation & Discrepancy Reporting | I | R | D | R | R | D |
| GRN, Batch/Lot, Inventory & Inventory Life-cycle Management | I | R | D | R | R | D |
| Picking List, Batch QR Scan & Inventory Update Implementation | I | D | D | S | S | D |
| FEFO/MLOR, Multi-Warehouse Allocation, Reservation & Optimistic Locking | I | D | S | S | S | S |
| Notification, Audit Trail, Batch Cronjob & Expired Batch Blocking | I | S | D | S | S | D |
| Backend, Web, Mobile & API Integration Development | I | R | D | D | D | D |
| Unit, Integration, System, Performance & Offline Testing | I | D | D | D | D | D |
| Bug Fixing, Refactoring, Deployment & Environment Configuration | I | D | D | D | D | D |
| Documentation Consolidation, Final Demo & Defense | I | D | S | S | S | S |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Mentor | chiltq | - Review works and documents - Give feedback - Evaluate progress and result | Weekly | Face to face, Google Meets, Zalo |
| Project team meeting | Team member | - Discuss about work and problem - Raise opinions - Check task list in Azure DevOps | 2–3 days/week | Face to face, Discord, Google Meets |

## 6. Configuration Management

The project applies configuration management practices to control changes in project documents and source code throughout the development process. The team uses shared tools to ensure that all members can access the latest versions, track modifications, and restore previous versions when necessary.

### 6.1 Document Management

- The team uses Google Drive as the primary platform for storing and managing project documents. All project-related documents are organized in shared folders that can be accessed by all team members.

- Document versions are managed using the following rules:

  - Each document includes a version number in the file name, for example: Project_Detail_v1.0, Project_Detail_v2.0.

  - A new version is created whenever significant content is added, modified, or removed.

  - Each document contains a Record of Changes table to record:

    - Date of change

    - Change type: Added / Modified / Deleted

    - Person in charge

    - Description of the change

  - Older versions are retained on Google Drive for traceability and rollback when needed.

  - Team members should update the document version and Record of Changes before sharing or using a revised document as the latest project reference.

  - Finalized documents are clearly identified to avoid confusion between working and approved versions.

### 6.2 Source Code Management

- The team uses Git and GitHub to manage project source code. All repositories are stored under a shared GitHub Organization so that source code ownership and access are managed at the team level instead of individual accounts.

- The source code is managed using the following practices:

  - Each project component is stored in a repository under the team GitHub Organization.

  - Git is used to track source code changes and maintain version history.

  - Team members develop new functions or fixes on separate branches instead of modifying the main branch directly.

  - Completed changes are submitted through Pull Requests for review before being merged.

  - Commit messages should clearly describe the implemented change or fixed issue.

  - The main branch contains stable and reviewed source code.

  - GitHub history is used to track modifications, identify contributors, compare versions, and restore previous code when necessary.

  - Access permissions to repositories are managed through the GitHub Organization to ensure that only authorized team members can modify project source code.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | React (Web Frontend), Flutter (Mobile App), ASP.NET Core Web API (Backend) |
| Database | Azure Database for PostgreSQL, SQLite (Mobile Local Cache) |
| IDEs/Editors | Visual Studio, Visual Code, Kiro |
| Diagramming | Draw.io, Mermaid.js |
| Documentation | Ms Office, Google Docs/Sheets/Slides, Google Drive |
| Version Control | GitHub Organization (Source Codes), Google Drive (Documents)) |
| Deployment server | Vercel (Web Frontend), Microsoft Azure (Backend & Worker – compute service not yet selected) |
| Project management | Azure DevOps |