FA26SE083 — PROJECT SCHEDULE

| Name | Duration | Start | Finish | Predecessors | Resource Names | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 1 FA26SE083 — FSCM Project Schedule v1.3 | 137 days | 04/08/ 2026 | 18/12/ 2026 |  | All members | Baseline v1.3: S1 19 Oct–1 Nov; S2 2–15 Nov; S3 16–22 Nov. 167 tasks: Backend 82, Portal 51, Mobile 34; 164 To Do, 3 In Progress. S4 backup: 23 Nov–18 Dec. Preparation phases retained. |
| 2 Project Start | 0 days | 04/08/ 2026 | 04/08/ 2026 |  | All members | Start of the original four-week preparation period. |
| 3 Initiation & Early Preparation (Stage 1) | 28 days | 04/08/ 2026 | 31/08/ 2026 | 2 | All members | Preparation weeks 1–4, before the official project term. |
| 4 Kick-off, role assignment and domain research | 14 days | 04/08/ 2026 | 17/08/ 2026 | 2 | All members; Nhan, Khiet | Deliverables: Team Charter, responsibility allocation and Domain Research Note. |
| 5 Technical spikes: concurrency, offline queue and Redis | 21 days | 04/08/ 2026 | 24/08/ 2026 | 4SS | Nhan, Son, Khiet | Deliverables: experimental repository and feasibility findings; retained from the original preparation plan. |
| 6 Draft scope, business analysis, ERD and architecture | 21 days | 11/08/ 2026 | 31/08/ 2026 | 4SS | All members | Deliverables: draft scope and MoSCoW priorities, business analysis, ERD and architecture. |
| 7 Set up repositories, CI, task board and wireframes | 14 days | 18/08/ 2026 | 31/08/ 2026 | 5SS | Nhan, Son; Hai, Hoang | Deliverables: buildable base code, Azure Board, Portal and Mobile wireframes. |
| 8 Planning & Requirements (Stage 2) | 21 days | 01/09/ 2026 | 21/09/ 2026 | 6;7 | All members | Original planning period retained for scope definition and Review 1 preparation. |
| 9 Finalize Scope Statement, MoSCoW and MVP | 14 days | 01/09/ 2026 | 14/09/ 2026 | 6 | All members | Deliverables: agreed scope boundaries and prioritized feature list. |
| 10 Business analysis v1.0 and preliminary API specification | 21 days | 01/09/ 2026 | 21/09/ 2026 | 9SS | Khiet, Hai; Nhan | Deliverables: business processes, use cases and preliminary API contracts. |
| 11 Architecture, ERD and Data Dictionary | 14 days | 01/09/ 2026 | 14/09/ 2026 | 6 | Nhan | Deliverables: Architecture Diagram, batch-level ERD and Data Dictionary. |
| 12 Database migrations, base code and sprint planning | 14 days | 08/09/ 2026 | 21/09/ 2026 | 7 | Nhan, Son; All members | Deliverables: migrations from an empty database, repository/CI setup, schedule and initial assignments. |
| 13 Review 1 — Scope & MVP | 0 days | 21/09/ 2026 | 21/09/ 2026 | 9;10;11;12 | All members | Original milestone retained. Deliverables: scope package, Review 1 slides and MVP demonstration plan. |
| 14 Software Design (Stage 3) | 55 days | 08/09/ 2026 | 01/11/ 2026 | 11SS | Nhan, Khiet, Hai | Design refinement continues through S1; align the SRS, diagrams and API contracts with Scope V10 and the current task tracker. |
| 15 Refine business processes, use cases and SRS | 55 days | 08/09/ 2026 | 01/11/ 2026 | 10SS | Khiet, Hai | Deliverables: updated SRS and business flows for the 12:00 run, goods/price approval, reservation, manual offline submission and batch pricing. |
| 16 Finalize module design, sequences and ERD | 14 days | 19/10/ 2026 | 01/11/ 2026 | 11;13 | Nhan | Deliverables: module/sequence diagrams, ERD and migrations aligned with Scope V10; no internal transfers or batch reassignment between orders. |
| 17 Finalize API contracts and core test cases | 14 days | 19/10/ 2026 | 01/11/ 2026 | 10;13 | Nhan, Khiet; All members | Deliverables: API contracts and tests for roles/scopes, MLOR Category/SKU, order approval, allocation, stock reservation and pricing. |

| Name | Duration | Start | Finish | Predecessors | Resource Names | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 18 Implementation (Stage 4) | 35 days | 19/10/ 2026 | 22/11/ 2026 | 13 | All members | S1/S2/S3: 64/68/35 tasks. Backend 82, Portal 51, Mobile 34. Follow Task_Tracking PICs and sprint assignments; S3 includes testing, fixes and deployment. |
| 19 Sprint 1 — Foundation, orders & inventory | 14 days | 19/10/ 2026 | 01/11/ 2026 | 13;16SS;17SS | All members | 64 tasks: Backend 31, Portal 21, Mobile 12. PIC totals: Nhan 8, Khiet 10, Hai 17, Son 13, Hoang 16. Foundation, order intake and inventory/payment setup. |
| 20 Authentication, users and master data | 14 days | 19/10/ 2026 | 01/11/ 2026 | 19SS | Khiet, Hai, Son, Hoang | F08–F23: Portal/Mobile login, six-role access, seeded Admin, users, profiles, products, warehouses, Sales regions, two-tab retailer profiles, MLOR Category/SKU and credit terms. |
| 21 Promotions, online orders and pre-cutoff approval | 14 days | 19/10/ 2026 | 01/11/ 2026 | 19SS;20SS | Nhan, Hai, Son, Hoang | F24–F28, F32, F36–F37: ordinary promotions, indicative prices, Sales orders, region checks, order lists/details and approval before cutoff. No batch selection or reservation at order intake. |
| 22 Receipts, QR labels, ETA and payments | 14 days | 19/10/ 2026 | 01/11/ 2026 | 19SS;20SS | All members | F39–F42, F45, F54–F56, F63: goods receipts/batches, QR printing/lookup, expiry job, transport rules, distances, shared ETA and COD/prepayment. Prepayment follows final price approval. |
| 23 Sprint 2 — Allocation & end-to-end business flow | 14 days | 02/11/ 2026 | 15/11/ 2026 | 19 | All members | 68 tasks: Backend 34, Portal 20, Mobile 14. PIC totals: Nhan 36, Khiet 9, Hai 6, Son 9, Hoang 8. Offline drafts, allocation/pricing, dispatch/receipt, receivables, loyalty and KPI. |
| 24 Manual offline submission, allocation and pricing | 14 days | 02/11/ 2026 | 15/11/ 2026 | 23SS;21;22 | All members | F29–F31, F33, F35, F46, F85, F87–F91, F98: manual offline submission; 12:00 allocation; MLOR/ETA filtering and weighted scoring; batch discounts/pricing; Admin approval then atomic reserve. Shortage orders need a new order/time. |
| 25 Picking, dispatch, receipt and receivables | 14 days | 02/11/ 2026 | 15/11/ 2026 | 23SS;24SS | All members | F43–F44, F57–F58, F60–F61, F64–F65, F92–F93, F96, F100–F101: stock lock, warehouse shipments, scans, whole-order readiness, dispatch, actual receipt, receivables, single settlement and verified manual refunds. |
| 26 Loyalty, gift redemption, KPI and rankings | 14 days | 02/11/ 2026 | 15/11/ 2026 | 23SS;25SS | All members | F69–F76, F78: loyalty program, receipt-based points, ledger, gifts/redemption, Sales KPI/ranking and best-selling products. Nhan owns loyalty; Hai/Khiet Backend and Son/Hoang Portal own KPI/rankings per tracker. |
| 27 Review 2 — Design & Sprint 1 Progress | 0 days | 26/10/ 2026 | 26/10/ 2026 | 14SS;19SS | All members | Original review date retained, within S1. Present design and available foundation progress; S1 ends 1 Nov, S2 ends 15 Nov, S3 ends 22 Nov. |
| 28 Sprint 3 — Completion, verification & handover | 7 days | 16/11/ 2026 | 22/11/ 2026 | 23 | All members | 35 tasks: Backend 17, Portal 10, Mobile 8. PIC totals: Nhan 11, Khiet 7, Hai 4, Son 8, Hoang 5. Complete remaining Medium tasks, test, fix, deploy and hand over; no new High features. |
| 29 Allocation controls, write-off and complaints | 7 days | 16/11/ 2026 | 22/11/ 2026 | 28SS;25 | Nhan, Khiet, Son | F38, F47, F59, F62, F94–F95: weight/radius settings, expiry write-off, delivery-cost estimate, complaints, cancellation after reserve before picking, run closure/report. No internal transfers or batch swaps. |
| 30 Overdue balances, dashboards and notifications | 7 days | 16/11/ 2026 | 22/11/ 2026 | 28SS;26 | Khiet, Hai, Son, Hoang | F66–F68, F77, F79–F81: overdue job, Sales/Retailer receivables, Mobile KPI/ranking, Admin dashboard, in-app and push notifications. Preserve the tracker PIC for each platform task. |
| 31 Allocation scenarios and FEFO comparison | 7 days | 16/11/ 2026 | 22/11/ 2026 | 28SS;24 | Nhan | F97, F99: test cutoff, shortage rollback, pricing, reservation/concurrency and dispatch exceptions; compare weighted greedy with FEFO on the same data and eligibility conditions. No retained priority for new shortage orders. |
| 32 Verification — Sprint 3 (Stage 5) | 7 days | 16/11/ 2026 | 22/11/ 2026 | 28SS;25;26 | Khiet, Hai, Son, Hoang | F82–F84: demo data, integration/permission tests, defect fixes and final deployment, all assigned to S3. Planned acceptance and handover by 22 Nov; S4 is contingency only. |
| 33 Review 3 — Progress Demo & Mock Defense | 0 days | 16/11/ 2026 | 16/11/ 2026 | 23;28SS | All members | Original review date retained, at S3 start. Demo completed S1/S2 flows and available S3 work; integration testing, fixes, deployment and handover are planned by 22 Nov. |
| 34 Seed demo data and test end-to-end workflows | 7 days | 16/11/ 2026 | 22/11/ 2026 | 32SS;31SS | Khiet, Hai, Hoang | F82–F83: Khiet seeds demo data; Hai tests Backend; Hoang tests Portal/Mobile. Cover order approval → allocation/pricing → Admin approval/reserve → picking → dispatch → actual receipt, plus payments, loyalty and manual offline submission. |
| 35 Transition (Stage 6) | 32 days | 17/11/ 2026 | 18/12/ 2026 | 33 | All members | Planned software deployment/handover by 22 Nov. Prepare thesis, manuals and defense materials alongside S3. S4 (23 Nov–18 Dec) is reserved for contingencies and final support. |
| 36 Fix defects and deploy the final release | 7 days | 16/11/ 2026 | 22/11/ 2026 | 34SS | Hai, Son | F84: Hai handles Backend fixes, migrations and deployment; Son handles Portal fixes/Vercel deployment and Mobile fixes/demo APK. Planned final release by 22 Nov; contingency repairs use S4 only if needed. |
| 37 Thesis, manuals and defense preparation | 28 days | 17/11/ 2026 | 14/12/ 2026 | 33;35SS | All members; Hai, Hoang; Nhan, Son | Original document owners/dates retained: thesis/manuals by 7 Dec; deployment guide, README, slides, Q&A and rehearsal by 14 Dec. Software evidence follows the S3 release. |
| 38 Sprint 4 — Contingency / backup window | 26 days | 23/11/ 2026 | 18/12/ 2026 | 32;36 | All members | No baseline feature tasks. Use only for approved spillover, defect fixes, retesting, deployment recovery or review feedback. Starts after S3; retains the original project end of 18 Dec. Defense milestone remains 14 Dec. |
| 39 Final Project Package & Defense | 0 days | 14/12/ 2026 | 14/12/ 2026 | 34;36;37 | All members | Original defense date retained. Deliverables: thesis, source/README, manuals, deployment guide, APK/online demo, slides, test evidence and records. S4 support may continue through 18 Dec. |